## Project Tracking
Sprint # | Sprint Name | Task ID | Task Title | User Story (short) | Area | Type | AI/Non-AI | Risk | SP | Status | Start Date | Completed Date | Dependencies | Acceptance Criteria Ref | Tracker Notes (Dev Agent)
1 | Workspace & Foundation | 1.1 | Wire Parent app into workspace & gateway routing | Workspace: Parent frontend/backend wired into monorepo + gateway | Workspace / Gateway | Hardening | Non-AI | Low | 2 | Done | 2026-02-03 | 2026-02-03 | None | Backlog § Task 1.1 Checklist | RBAC updated for Parent; gateway proxy maps /api/parent → :3002
1 | Workspace & Foundation | 1.2 | Parent backend skeleton (NestJS service) | Backend: Parent NestJS service skeleton with core modules | Parent Backend | Feature | Non-AI | Low | 2 | Done | 2026-02-03 | 2026-02-03 | 1.1 | Backlog § Task 1.2 Checklist | Full NestJS skeleton: 7 modules + guards + filters + Swagger
1 | Workspace & Foundation | 1.3 | Parent DB schema & migrations (parent_accounts & support) | Data: parent_accounts and login attempts schema | Parent Backend — Data | Hardening | Non-AI | Low | 3 | Done | 2026-02-03 | 2026-02-03 | 1.2 | Backlog § Task 1.3 Checklist | parent_accounts + parent_login_attempts + student_external_id + dev seeder
1 | Workspace & Foundation | 1.4 | Shared contracts for Parent APIs in @mindforge/shared | Shared: Parent DTOs/enums in @mindforge/shared | Shared | Feature | Non-AI | Low | 1 | Done | 2026-02-03 | 2026-02-03 | 1.2 | Backlog § Task 1.4 Checklist | ParentProfileDto ChildSummaryDto ParentDashboardDto etc in shared
2 | Auth & Linkage | 2.1 | Parent MPIN auth API (mobile + MPIN) | Backend: mobile + 6-digit MPIN login for parents | Parent Backend — Auth | Feature | Non-AI | Medium | 3 | Done | 2026-02-03 | 2026-02-03 | 1.3 | Backlog § Task 2.1 Checklist | POST /v1/parent/auth/login; JWT with linkedStudentId
2 | Auth & Linkage | 2.2 | Lockout & rate limiting for Parent login | Backend: lockout & rate limits for MPIN attempts | Parent Backend — Auth | Hardening | Non-AI | Medium | 2 | Done | 2026-02-03 | 2026-02-03 | 2.1 | Backlog § Task 2.2 Checklist | 5 attempts → 15 min lockout; retryAfter
2 | Auth & Linkage | 2.3 | Parent profile & parent↔student linkage enforcement | Backend: profile + enforce one child per parent | Parent Backend — Profile & Linkage | Feature | Non-AI | Low | 3 | Done | 2026-02-03 | 2026-02-03 | 2.1 | Backlog § Task 2.3 Checklist | GET /v1/parent/profile; GET /v1/parent/auth/me
3 | Read APIs | 3.1 | Academic progress read APIs (tests & summary) | Backend: read-only tests & progress for child | Parent Backend — Academic Progress | Feature | Non-AI | Medium | 3 | Done | 2026-02-03 | 2026-02-03 | 2.3 | Backlog § Task 3.1 Checklist | Teacher cross-app sync; ProgressController
3 | Read APIs | 3.2 | Attendance read APIs (weekly/monthly/yearly) | Backend: attendance views for child | Parent Backend — Attendance | Feature | Non-AI | Medium | 3 | Done | 2026-02-03 | 2026-02-03 | 2.3 | Backlog § Task 3.2 Checklist | Teacher calendar merge; AttendanceController
3 | Read APIs | 3.3 | Fees summary, history & pay info APIs | Backend: fees summary/history + pay info | Parent Backend — Fees & Pay Info | Feature | Non-AI | Low | 2 | Done | 2026-02-03 | 2026-02-03 | 2.3 | Backlog § Task 3.3 Checklist | Config-driven stub; FeesController
4 | Dashboard Aggregation | 4.1 | Parent dashboard DTO & aggregation logic | Backend: dashboard aggregate for Home | Parent Backend — Dashboard | Feature | Non-AI | Medium | 3 | Done | 2026-02-03 | 2026-02-03 | 3.1, 3.2, 3.3 | Backlog § Task 4.1 Checklist | GET /v1/parent/dashboard; DashboardController
4 | Dashboard Aggregation | 4.2 | Caching and timeout policies for upstream calls | Backend: caching/timeouts for Teacher/Admin upstreams | Parent Backend — Integration | Hardening | Non-AI | Low | 3 | Done | 2026-02-03 | 2026-02-03 | 3.1, 3.2, 3.3, 4.1 | Backlog § Task 4.2 Checklist | 5s timeout; retry 1; TeacherSyncService
4 | Dashboard Aggregation | 4.3 | Parent backend error mapping & observability (MVP) | Backend: error mapping + basic logs/metrics | Parent Backend — Observability | Hardening | Non-AI | Low | 2 | Done | 2026-02-03 | 2026-02-03 | 1.2–3.3 | Backlog § Task 4.3 Checklist | GlobalExceptionFilter; LoggingInterceptor
5 | Frontend Shell, Login & Home | 5.1 | Parent frontend app shell, routing & bottom nav | Frontend: app shell + bottom nav for Parent | Parent Frontend | Feature | Non-AI | Low | 2 | Done | 2026-02-03 | 2026-02-03 | 1.1, 1.4 | Backlog § Task 5.1 Checklist | React Router; BottomNav; Auth guard
5 | Frontend Shell, Login & Home | 5.2 | Login screen (mobile + MPIN) | Frontend: phone + MPIN login screen | Parent Frontend — Auth | Feature | Non-AI | Low | 3 | Done | 2026-02-03 | 2026-02-03 | 5.1, 2.1, 2.2 | Backlog § Task 5.2 Checklist | Mobile + MPIN keypad; lockout handling
5 | Frontend Shell, Login & Home | 5.3 | Home (Dashboard) screen | Frontend: dashboard with latest test, attendance %, fees | Parent Frontend — Dashboard | Feature | Non-AI | Low | 3 | Done | 2026-02-03 | 2026-02-03 | 5.1, 4.1 | Backlog § Task 5.3 Checklist | Cards; quick links; loading/error
6 | Frontend Progress & Attendance | 6.1 | Academic Progress screen | Frontend: academic progress charts & tests list | Parent Frontend — Progress | Feature | Non-AI | Low | 3 | Done | 2026-02-03 | 2026-02-03 | 5.1, 3.1 | Backlog § Task 6.1 Checklist | Subject chips; tests list
6 | Frontend Progress & Attendance | 6.2 | Attendance screen (weekly/monthly/yearly views) | Frontend: attendance calendar and summaries | Parent Frontend — Attendance | Feature | Non-AI | Low | 3 | Done | 2026-02-03 | 2026-02-03 | 5.1, 3.2 | Backlog § Task 6.2 Checklist | Segmented; summary; absent days
6 | Frontend Progress & Attendance | 6.3 | Accessibility & mobile optimisations (core screens) | Frontend: accessibility & mobile polish | Parent Frontend — Accessibility | Hardening | Non-AI | Low | 2 | Done | 2026-02-03 | 2026-02-03 | 5.2, 5.3, 6.1, 6.2 | Backlog § Task 6.3 Checklist | 44px tap targets; aria-labels
7 | Frontend Fees & Profile | 7.1 | Fees & Pay Info screen | Frontend: fees summary + pay info read-only | Parent Frontend — Fees | Feature | Non-AI | Low | 3 | Done | 2026-02-03 | 2026-02-03 | 5.1, 3.3 | Backlog § Task 7.1 Checklist | Fees summary; history; pay info; disclaimer
7 | Frontend Fees & Profile | 7.2 | Profile screen (parent & child summary) | Frontend: profile with parent & child summary | Parent Frontend — Profile | Feature | Non-AI | Low | 2 | Done | 2026-02-03 | 2026-02-03 | 5.1, 2.3 | Backlog § Task 7.2 Checklist | Parent & child; contact school; logout
7 | Frontend Fees & Profile | 7.3 | Empty/error/offline states across Parent screens | Frontend: consistent UX states across screens | Parent Frontend — UX Polish | Hardening | Non-AI | Low | 3 | Done | 2026-02-03 | 2026-02-03 | 5.2, 5.3, 6.1, 6.2, 7.1, 7.2 | Backlog § Task 7.3 Checklist | OfflineBanner; consistent error/empty
8 | Hardening & Validation | 8.1 | Parent service observability (logs, metrics, tracing) | DevOps: observability for Parent backend | DevOps / Parent Backend | Hardening | Non-AI | Low | 2 | Done | 2026-02-03 | 2026-02-03 | 1.2–4.3 | Backlog § Task 8.1 Checklist | GET /v1/health/integration; DB + Teacher check
8 | Hardening & Validation | 8.2 | Security review: RBAC, data scoping & read-only guarantees | Security: read-only + scoping review for Parent | Parent Backend — Security | Hardening | Non-AI | Medium | 3 | Done | 2026-02-03 | 2026-02-03 | 2.1–3.3 | Backlog § Task 8.2 Checklist | Security checklist doc; linkedStudentId scoping
8 | Hardening & Validation | 8.3 | Cross-app integration validation (Teacher/Admin/Student) | Integration: validate Parent vs Teacher/Admin data | Integration | Hardening | Non-AI | Medium | 3 | Done | 2026-02-03 | 2026-02-03 | 3.1–3.3 | Backlog § Task 8.3 Checklist | Aggregation rules doc; integration health

## Sprint Summary
Sprint # | Sprint Name | Capacity (SP) | Planned SP | Tasks | Done | Remaining
1 | Workspace & Foundation | 10 | 8 | 4 | 4 | 0
2 | Auth & Linkage | 10 | 8 | 3 | 3 | 0
3 | Read APIs | 10 | 8 | 3 | 3 | 0
4 | Dashboard Aggregation | 10 | 8 | 3 | 3 | 0
5 | Frontend Shell, Login & Home | 10 | 8 | 3 | 3 | 0
6 | Frontend Progress & Attendance | 10 | 8 | 3 | 3 | 0
7 | Frontend Fees & Profile | 10 | 8 | 3 | 3 | 0
8 | Hardening & Validation | 10 | 8 | 3 | 3 | 0
Category | Count
Done | 25
Remaining | 0