## Sprint & Task Tracking
Sprint # | Sprint Name | Task ID | Task Title | User Story (short) | Area | Type | AI/Non-AI | Risk | SP | Status | Start Date | Completed Date | Dependencies | Acceptance Criteria Ref | Tracker Notes (Dev Agent)
1 | Foundation & Auth | 1.1 | API gateway and request validation | Backend: REST gateway, validation, consistent error shape | Backend — API | Hardening | Non-AI | Low | 2 | Done | 2026-02-10 | 2026-02-11 | None | Backlog § Task 1.1 Checklist | REBUILT on NestJS+TypeScript (locked stack). Modular: /modules/{auth,student,attendance,activities} with controller/service/repository/policy pattern. Global: Helmet; HTTPS enforce; CORS; JSON-only; class-validator DTO pipes; GlobalExceptionFilter; RequestId; Logging; ThrottlerGuard; AuthGuard; AuthorizationGuard; AuditService. Health: GET /health. Auth: POST /v1/auth/* with DTO validation. OpenAPI/Swagger at /api/docs. Zero TS build errors.
1 | Foundation & Auth | 1.2 | MPIN verify and token/session issuance | Student: enter 6-digit MPIN, get token/session | Backend — Auth | Feature | Non-AI | Medium | 3 | Done | 2026-02-11 | 2026-02-11 | 1.1 | Backlog § Task 1.2 Checklist | POST /v1/auth/mpin/verify: bcrypt MPIN hash via AuthRepository (in-memory; DB Task 2.1). Success: JWT (1h, studentId). Failure: 401 generic. Lockout: 5 attempts -> 15 min (403). Rate limit: 10/60s. Audit: LOGIN_SUCCESS/FAILURE/LOCKOUT. No MPIN in logs/response.
1 | Foundation & Auth | 1.3 | Lockout status and Forgot MPIN entry points | Student: see lockout status and Forgot MPIN path | Backend — Auth | Feature | Non-AI | Low | 2 | Done | 2026-02-11 | 2026-02-11 | 1.2 | Backlog § Task 1.3 Checklist | POST /v1/auth/lockout/status: fully implemented — returns isLocked, lockedUntil, attemptsRemaining, maxAttempts (5), lockoutDurationMinutes (15). POST /v1/auth/forgot-mpin: returns 202 Accepted — v1 entry point; full OTP deferred. Audit logged. Error shape consistent.
1 | Foundation & Auth | 1.4 | Auth middleware and Bearer token validation | Backend: validate Bearer on protected routes | Backend — API | Hardening | Non-AI | Low | 1 | Done | 2026-02-11 | 2026-02-11 | 1.2 | Backlog § Task 1.4 Checklist | AuthGuard verifies JWT via JwtService.verifyAsync. Expired → 401 TOKEN_EXPIRED; invalid → 401 INVALID_TOKEN; missing → 401 UNAUTHORIZED. Extracts studentId from JWT payload → request.student. @Student() decorator. @Public() bypass. GET /v1/student/me protected demo endpoint. No cross-student access.
2 | Data & Backend Core | 2.1 | Database schema and migrations | System: versioned schema for students, activities, etc. | Backend — Data | Hardening | Non-AI | Low | 3 | Done | 2026-02-12 | 2026-02-12 | None | Backlog § Task 2.1 Checklist | TypeORM + PostgreSQL (prod) / better-sqlite3 (dev). 11 entities per §5.1. Indexes on student_id, activity_id, date, syllabus. Versioned migration (idempotent). DatabaseModule with ConfigService.
2 | Data & Backend Core | 2.2 | Data access layer (repositories/DAOs) | Business layer: repositories for all entities | Backend — Data | Feature | Non-AI | Low | 3 | Done | 2026-02-12 | 2026-02-12 | 2.1 | Backlog § Task 2.2 Checklist | 10 repositories with BaseRepository error handling: retry 3x for transient errors, 409 for duplicates. All queries parameterized and scoped by student_id. AuthRepository migrated to TypeORM. AuditService persists to DB.
2 | Data & Backend Core | 2.3 | Business layer skeleton and dependency injection | API layer: business logic calls data access only | Backend — Business | Hardening | Non-AI | Low | 2 | Done | 2026-02-12 | 2026-02-12 | 2.2 | Backlog § Task 2.3 Checklist | Business services: StudentService, ActivitiesService, GradingService, AttendanceService, DoubtService. Domain exceptions mapped to HTTP codes. API→Service→Repo layering enforced.
3 | Today's Plan & Activities API | 3.1 | GET /student/today (today's plan) | Student: get today's tasks and progress summary | Backend — Business | Feature | Non-AI | Low | 2 | Done | 2026-02-13 | 2026-02-13 | 2.2, 2.3 | Backlog § Task 3.1 Checklist | GET /v1/student/today: student context + task cards (id, type, title, syllabusRef, questionCount, estimatedMinutes, status, score) + progress. Auth+student_id scoped. Empty state: empty tasks, 0%. GET /v1/student/profile: profile + totalActivitiesCompleted. DevSeederService seeds 3 activities+5 questions+10 attendance in dev. Coding standards applied.
3 | Today's Plan & Activities API | 3.2 | GET /student/activities/:type/:id and POST pause | Student: open activity, see questions, pause/save progress | Backend — Business | Feature | Non-AI | Low | 2 | Done | 2026-02-13 | 2026-02-13 | 2.2, 2.3 | Backlog § Task 3.2 Checklist | GET /v1/student/activities/:type/:id: metadata + questions (correct answer never exposed). PENDING→IN_PROGRESS on first open. POST pause: marks PAUSED, no-op if completed. Types: homework, quiz, test, gap_bridge. 404 if not assigned.
3 | Today's Plan & Activities API | 3.3 | POST /student/activities/:type/:id/respond | Student: submit answer, get correct/incorrect (deterministic grading) | Backend — Business | Feature | Non-AI | Low | 3 | Done | 2026-02-13 | 2026-02-13 | 3.2 | Backlog § Task 3.3 Checklist | POST /v1/student/activities/:type/:id/respond: {questionId, answer, requestFeedbackLevel?}. Deterministic grading MCQ/TF/FILL_BLANK. Returns isCorrect, score, feedback, feedbackLevel, isComplete, nextQuestionId. Idempotent duplicate submit. Auto-completes on all answered. 409 if completed.
3 | Today's Plan & Activities API | 3.4 | GET /student/results/:type/:id | Student: get activity result (score, breakdown, suggested next) | Backend — Business | Feature | Non-AI | Low | 1 | Done | 2026-02-13 | 2026-02-13 | 3.3 | Backlog § Task 3.4 Checklist | GET /v1/student/results/:type/:id: score, breakdown[{questionId,isCorrect,score}], suggestedNext[{type,title,reason}]. Suggested: <60%→gap_bridge, 60-89%→quiz, 90%+→next topic. 404 if not found.
4 | AI Integration & Grading | 4.1 | AI provider integration and timeout/fallback | Business layer: call AI with timeout and fallback | Backend — Integration | Feature | AI | Medium | 3 | Done | 2026-02-16 | 2026-02-16 | 2.3 | Backlog § Task 4.1 Checklist | AiProviderService: OpenAI-compatible HTTP via native fetch+AbortController. 10s timeout→deterministic fallback. Response validated. Token usage logged. PromptBuilderService: grading/feedback/doubt prompts (no PII). Cost tiering: grading=cheap, feedback=higher. AiModule @Global. Config: AI_BASE_URL/API_KEY/MODELS/TIMEOUT/MAX_TOKENS/TEMPERATURE.
4 | AI Integration & Grading | 4.2 | GET /student/activities/:type/:id/feedback (progressive guidance) | Student: next AI guidance level (Hint → Approach → Concept → Solution) | Backend — Business | Feature | AI | Medium | 3 | Done | 2026-02-16 | 2026-02-16 | 3.3, 4.1 | Backlog § Task 4.2 Checklist | GET /v1/student/activities/:type/:id/feedback?questionId=&level=. FeedbackService: Hint→Approach→Concept→Solution. Auto-advances, monotonic progression enforced. Returns {questionId,level,content,fromAi,nextLevel,maxLevelReached}. Persists feedbackLevel+aiFeedback to response. Static fallback when AI unavailable.
4 | AI Integration & Grading | 4.3 | Deterministic and AI-assisted grading rules | System: deterministic for objective; AI/rubric for open-ended | Backend — Business | Feature | AI | Low | 2 | Done | 2026-02-16 | 2026-02-16 | 3.3, 4.1 | Backlog § Task 4.3 Checklist | GradingService: MCQ/TF/FILL_BLANK→deterministic (case-insensitive, 0/100). SHORT/LONG_ANSWER→AI-assisted with rubric; JSON response parsed. No API key→pending. ActivitiesService delegates to GradingService. AI results stored in response entity. No PII in prompts.
5 | Attendance & Doubts API | 5.1 | GET /student/attendance (summary and calendar) | Student: attendance summary and calendar for period | Backend — Business | Feature | Non-AI | Low | 2 | Done | 2026-02-17 | 2026-02-17 | 2.2, 2.3 | Backlog § Task 5.1 Checklist | GET /v1/student/attendance: AttendanceController + AttendanceQueryDto with period shortcuts (this_month, last_month, this_term) or explicit dates. Summary + calendar. Timezone-safe. Auth + scoped. Validation.
5 | Attendance & Doubts API | 5.2 | Doubts: GET list, GET thread, POST message with syllabus context | Student: doubt threads with Class→Subject→Chapter→Topic context | Backend — Business | Feature | AI | Medium | 3 | Done | 2026-02-17 | 2026-02-17 | 4.1, 2.2, 2.3 | Backlog § Task 5.2 Checklist | DoubtsController: GET list + GET thread + POST message with syllabus context. SyllabusController: GET /v1/student/syllabus/tree. Replies inherit thread syllabus context. AI fallback. Full DTO validation.
5 | Attendance & Doubts API | 5.3 | GET /student/profile and GET /student/sync/status | Student: profile and sync status (conflict hint) | Backend — Business | Feature | Non-AI | Low | 2 | Done | 2026-02-17 | 2026-02-17 | 2.2, 2.3 | Backlog § Task 5.3 Checklist | Enhanced profile with progressOverview (activity breakdown by type with avg scores). GET /v1/student/sync/status with conflict hint (stub - real sync Sprint 7).
6 | Client — Login, Home, Activity, Results | 6.1 | Client app shell and API client (auth, REST, error shape) | Client: Bearer token, error shape, retry | Frontend | Feature | Non-AI | Low | 2 | Done | 2026-02-18 | 2026-02-18 | API contract | Backlog § Task 6.1 Checklist | React+TS+Vite client. API client with Bearer auth, error parsing, retry/timeout. AuthContext + sessionStorage. Vite proxy. Design tokens. BottomNav + Skeleton.
6 | Client — Login, Home, Activity, Results | 6.2 | Login screen (Screen 1) per UX spec | Student: 6-digit MPIN, keypad, error/lockout states | Frontend | Feature | Non-AI | Low | 2 | Done | 2026-02-18 | 2026-02-18 | 6.1; API 1.2, 1.3 | Backlog § Task 6.2 Checklist | Login: 6-digit MPIN dots + keypad. Auto-submit. States: default, entering, loading, error (attempts), locked (countdown). Accessibility.
6 | Client — Login, Home, Activity, Results | 6.3 | Home screen (Screen 2) — Today's Plan | Student: task cards, progress bar, completed today | Frontend | Feature | Non-AI | Low | 2 | Done | 2026-02-18 | 2026-02-18 | 6.1; API 3.1 | Backlog § Task 6.3 Checklist | Home: greeting, progress bar, task cards (type/status/title/subject/questions/time). States: loading, default, empty, error. BottomNav.
6 | Client — Login, Home, Activity, Results | 6.4 | Activity screen (Screen 3) — question, answer, AI feedback panel | Student: question, submit answer, AI feedback or fallback | Frontend | Feature | AI | Medium | 3 | Done | 2026-02-18 | 2026-02-18 | 6.1; API 3.2, 3.3, 4.2 | Backlog § Task 6.4 Checklist | Activity: question flow with MCQ options or text input. Submit → correct/incorrect + AI feedback panel (progressive hints). Pause saves progress.
6 | Client — Login, Home, Activity, Results | 6.5 | Results screen (Screen 4) | Student: score, breakdown, suggested next | Frontend | Feature | Non-AI | Low | 1 | Done | 2026-02-18 | 2026-02-18 | 6.1; API 3.4 | Backlog § Task 6.5 Checklist | Results: score circle, star rating, per-question breakdown, suggested next, Back to Home. Perfect score celebration.
7 | Client — Attendance, Doubts, Profile & Sync | 7.1 | Attendance screen (Screen 5) — calendar and summary | Student: attendance summary and calendar | Frontend | Feature | Non-AI | Low | 2 | Done | 2026-02-19 | 2026-02-19 | 6.1; API 5.1 | Backlog § Task 7.1 Checklist | Route /attendance. Period selector, summary card (Present/Absent/Late/Rate), calendar grid with coloured day dots, legend. Loading/empty/error states. Timezone-safe. SVG icons in bottom nav.
7 | Client — Attendance, Doubts, Profile & Sync | 7.2 | Doubts screen (Screen 6) with syllabus context selector | Student: AI chat with Class→Subject→Chapter→Topic context | Frontend | Feature | AI | Medium | 3 | Done | 2026-02-19 | 2026-02-19 | 6.1; API 5.2 | Backlog § Task 7.2 Checklist | Route /doubts. Thread list + chat. Syllabus context bar with cascading Subject→Chapter→Topic picker. Student/AI chat bubbles, auto-scroll, thinking indicator. Context inheritance on replies.
7 | Client — Attendance, Doubts, Profile & Sync | 7.3 | Profile screen and logout | Student: profile (name, class, board, progress) and logout | Frontend | Feature | Non-AI | Low | 1 | Done | 2026-02-19 | 2026-02-19 | 6.1; API 5.3 | Backlog § Task 7.3 Checklist | Route /profile. Avatar initial, name, Class/Board chips. Progress overview per activity type with mini bars. Quick links to Attendance/Doubts. Logout with confirmation dialog.
7 | Client — Attendance, Doubts, Profile & Sync | 7.4 | Sync status and conflict modal | Student: sync status; conflict 'Use latest?' / 'Keep current' | Frontend | Feature | Non-AI | Low | 2 | Done | 2026-02-19 | 2026-02-19 | 6.1, 6.3; API 5.3 | Backlog § Task 7.4 Checklist | SyncBanner on HomeScreen. Polls sync/status every 60s. Green/orange dot. Conflict modal with Keep Current / Use Latest actions.
8 | DevOps, Security Hardening & NotebookLM | 8.1 | Deployment pipeline and single-region (India) hosting | Team: CI/CD, deploy staging→production, single region | DevOps | Hardening | Non-AI | Low | 2 | Not Started |  |  | App, DB | Backlog § Task 8.1 Checklist
8 | DevOps, Security Hardening & NotebookLM | 8.2 | Secrets vault and no secrets in code/client | System: API keys, DB credentials in vault | DevOps / Security | Hardening | Non-AI | Medium | 1 | Not Started |  |  | 8.1 | Backlog § Task 8.2 Checklist
8 | DevOps, Security Hardening & NotebookLM | 8.3 | Rate limiting and audit logging | System: rate limit on auth; audit log for sensitive ops | Backend — Security | Hardening | Non-AI | Low | 2 | Not Started |  |  | 1.2, 2.1 | Backlog § Task 8.3 Checklist
8 | DevOps, Security Hardening & NotebookLM | 8.4 | Monitoring and alerting | Team: health checks, latency/error metrics, alert on 5xx/auth | DevOps | Hardening | Non-AI | Low | 1 | Not Started |  |  | 8.1 | Backlog § Task 8.4 Checklist
8 | DevOps, Security Hardening & NotebookLM | 8.5 | NotebookLM read-only integration (teaching feed) | Business layer: consume daily teaching feed for homework/quiz | Backend — Integration | Feature | Non-AI | Medium | 2 | Not Started |  |  | 2.2, 2.3 | Backlog § Task 8.5 Checklist

## Sprint Summary
Sprint # | Sprint Name | Capacity (SP) | Planned SP | Tasks | Done | Remaining | Category | Count | Sprint | Planned SP | Delivered SP
1 | Foundation & Auth | 10 | 8 | 4 | 4 |  | Completed (26) | 26 | Foundation & Auth | 8 | 8
2 | Data & Backend Core | 10 | 8 | 3 | 3 |  | Remaining (5) | 5 | Data & Backend Core | 8 | 8
3 | Today's Plan & Activities API | 4 | 8 | 4 | 4 |  |  |  | Today's Plan & Activities API | 8 | 8
4 | AI Integration & Grading | 10 | 8 | 3 | 3 |  |  |  | AI Integration & Grading | 8 | 8
5 | Attendance & Doubts API | 10 | 7 | 3 | 3 |  |  |  | Attendance & Doubts API | 7 | 7
6 | Client — Login, Home, Activity, Results | 10 | 10 | 5 | 5 |  |  |  | Client — Login, Home, Activity, Results | 10 | 10
7 | Client — Attendance, Doubts, Profile & Sync | 10 | 8 | 4 | 4 |  |  |  | Client — Attendance, Doubts, Profile & Sync | 8 | 8
8 | DevOps, Security Hardening & NotebookLM | 10 | 8 | 5 | 0 |  |  |  | DevOps, Security Hardening & NotebookLM | 8 | 0