## Project Tracking
Sprint # | Sprint Name | Task ID | Task Title | User Story (short) | Area | Type | AI/Non-AI | Risk | SP | Status | Start Date | Completed Date | Dependencies | Acceptance Criteria Ref | Tracker Notes (Dev Agent)
1 | Workspace & Foundation | 1.1 | Wire Admin app into workspace & gateway routing | Workspace: Admin frontend/backend wired into monorepo + gateway | Workspace / Gateway | Hardening | Non-AI | Low | 2 | Done | 2026-02-01 | 2026-02-01 | None | Backlog § Task 1.1 Checklist
1 | Workspace & Foundation | 1.2 | Admin backend skeleton (NestJS service) | Backend: Admin NestJS service skeleton with core modules | Admin Backend | Feature | Non-AI | Low | 2 | Done | 2026-02-01 | 2026-02-01 | 1.1 | Backlog § Task 1.2 Checklist
1 | Workspace & Foundation | 1.3 | Admin DB schema & migrations (user approval, fees & payments) | Data: admin-owned tables for approvals, fees, payments | Admin Backend — Data | Hardening | Non-AI | Medium | 3 | Done | 2026-02-01 | 2026-02-01 | 1.2 | Backlog § Task 1.3 Checklist
1 | Workspace & Foundation | 1.4 | Shared contracts for Admin APIs in @mindforge/shared | Shared: Admin DTOs/enums in @mindforge/shared | Shared | Feature | Non-AI | Low | 1 | Done | 2026-02-01 | 2026-02-01 | 1.2 | Backlog § Task 1.4 Checklist
2 | User Approval & Lifecycle | 2.1 | User approval APIs (pending → active/disabled) | Backend: approve/reject/activate/deactivate users | Admin Backend — User Management | Feature | Non-AI | Medium | 3 | Done | 2026-02-01 | 2026-02-01 | 1.3 | Backlog § Task 2.1 Checklist
2 | User Approval & Lifecycle | 2.2 | Default MPIN and first-login change flagging | Backend: default 000000 MPIN + must-change-on-first-login flag | Admin Backend — User Management | Feature | Non-AI | Medium | 3 | Done | 2026-02-01 | 2026-02-01 | 2.1 | Backlog § Task 2.2 Checklist
2 | User Approval & Lifecycle | 2.3 | User account status & audit logging | Backend: audit logs for account status changes | Admin Backend — Audit Trail | Hardening | Non-AI | Medium | 2 | Done | 2026-02-01 | 2026-02-01 | 2.1 | Backlog § Task 2.3 Checklist
3 | Fees Config & Payment Info | 3.1 | Grade fee configuration APIs | Backend: CRUD + propagation for grade fee configs | Admin Backend — Fees | Feature | Non-AI | Medium | 3 | Done | 2026-02-01 | 2026-02-01 | 1.3 | Backlog § Task 3.1 Checklist
3 | Fees Config & Payment Info | 3.2 | Extra subject fee configuration APIs | Backend: per-student extra subject fee configs | Admin Backend — Fees | Feature | Non-AI | Medium | 3 | Done | 2026-02-01 | 2026-02-01 | 1.3 | Backlog § Task 3.2 Checklist
3 | Fees Config & Payment Info | 3.3 | Payment Info configuration APIs (QR, UPI, bank details) | Backend: config for Parent Pay Info (QR/UPI/bank) | Admin Backend — Payment Info | Feature | Non-AI | Low | 2 | Done | 2026-02-01 | 2026-02-01 | 1.3 | Backlog § Task 3.3 Checklist
4 | Payment Entry & Ledger | 4.1 | Fee payment entry APIs (create & edit) | Backend: record/correct fee payments | Admin Backend — Payments | Feature | Non-AI | Medium | 3 | Done | 2026-02-01 | 2026-02-01 | 1.3, 3.1, 3.2 | Backlog § Task 4.1 Checklist
4 | Payment Entry & Ledger | 4.2 | Fee summary and history APIs for Admin & Parent | Backend: fee summary/history for Admin & Parent | Admin Backend — Payments | Feature | Non-AI | Medium | 3 | Done | 2026-02-01 | 2026-02-01 | 4.1 | Backlog § Task 4.2 Checklist
4 | Payment Entry & Ledger | 4.3 | Admin fee KPIs & collection reports (backend only) | Backend: fee KPIs & collection over time | Admin Backend — Analytics | Feature | Non-AI | Low | 2 | Done | 2026-02-01 | 2026-02-01 | 4.2 | Backlog § Task 4.3 Checklist
5 | Frontend Shell, Dashboard & Users | 5.1 | Admin frontend app shell & sidebar navigation | Frontend: app shell + sidebar nav for Admin | Admin Frontend | Feature | Non-AI | Low | 2 | Done | 2026-02-01 | 2026-02-01 | 1.1, 1.4 | Backlog § Task 5.1 Checklist
5 | Frontend Shell, Dashboard & Users | 5.2 | Dashboard screen | Frontend: dashboard with KPIs, approvals table, fee chart | Admin Frontend — Dashboard | Feature | Non-AI | Low | 3 | Done | 2026-02-01 | 2026-02-01 | 5.1, 2.1, 4.3 | Backlog § Task 5.2 Checklist
5 | Frontend Shell, Dashboard & Users | 5.3 | Users screen (approvals & account statuses) | Frontend: Users screen for approvals & status management | Admin Frontend — Users | Feature | Non-AI | Medium | 3 | Done | 2026-02-01 | 2026-02-01 | 5.1, 2.1, 2.2, 2.3 | Backlog § Task 5.3 Checklist
6 | Frontend Fees & Payments | 6.1 | Fees configuration screen (grade & extra subject) | Frontend: grade fees + extra subject fees screen | Admin Frontend — Fees | Feature | Non-AI | Medium | 3 | Done | 2026-02-01 | 2026-02-01 | 5.1, 3.1, 3.2 | Backlog § Task 6.1 Checklist
6 | Frontend Fees & Payments | 6.2 | Payments ledger & entry screen | Frontend: payments ledger + record/edit flows | Admin Frontend — Payments | Feature | Non-AI | Medium | 3 | Done | 2026-02-01 | 2026-02-01 | 5.1, 4.1, 4.2 | Backlog § Task 6.2 Checklist
6 | Frontend Fees & Payments | 6.3 | Accessibility & table performance tuning | Frontend: accessibility + performance for tables/modals | Admin Frontend — Accessibility | Hardening | Non-AI | Low | 2 | Done | 2026-02-01 | 2026-02-01 | 5.2, 5.3, 6.1, 6.2 | Backlog § Task 6.3 Checklist
7 | Frontend Payment Info & Audit | 7.1 | Payment Info configuration screen | Frontend: Payment Info screen for QR/UPI/bank | Admin Frontend — Payment Info | Feature | Non-AI | Low | 3 | Done | 2026-02-01 | 2026-02-01 | 5.1, 3.3 | Backlog § Task 7.1 Checklist
7 | Frontend Payment Info & Audit | 7.2 | Audit Logs screen (simple v1) | Frontend: basic audit logs table | Admin Frontend — Audit Logs | Feature | Non-AI | Low | 2 | Done | 2026-02-01 | 2026-02-01 | 2.3, 3.1, 3.2, 3.3, 4.1, 4.3 | Backlog § Task 7.2 Checklist
7 | Frontend Payment Info & Audit | 7.3 | Empty/error/offline states across Admin screens | Frontend: consistent UX states across Admin | Admin Frontend — UX Polish | Hardening | Non-AI | Low | 3 | Done | 2026-02-01 | 2026-02-01 | 5.2, 5.3, 6.1, 6.2, 7.1, 7.2 | Backlog § Task 7.3 Checklist
8 | Hardening & Validation | 8.1 | Admin service observability (logs, metrics, tracing) | DevOps: observability for Admin backend | DevOps / Admin Backend | Hardening | Non-AI | Low | 2 | Done | 2026-02-01 | 2026-02-01 | 1.2–4.3 | Backlog § Task 8.1 Checklist
8 | Hardening & Validation | 8.2 | Security review: RBAC, approval states & fee/payment changes | Security: review of Admin RBAC and operations | Admin Backend — Security | Hardening | Non-AI | Medium | 3 | Done | 2026-02-01 | 2026-02-01 | 2.1–4.3 | Backlog § Task 8.2 Checklist
8 | Hardening & Validation | 8.3 | Cross-app integration validation (Student/Teacher/Parent) | Integration: validate Admin vs other apps | Integration | Hardening | Non-AI | Medium | 3 | Done | 2026-02-01 | 2026-02-01 | 2.1–4.3 | Backlog § Task 8.3 Checklist